## Slide 1: PROJECT MANAGEMENT PLAN. Development Of Agricultural Farm and Marketing Plan
Prepared by:
Role: Junior Project Manager
Lagos,Nigeria
Date: May 2026
TS Academy- PM Capstone Submission
Opeyemi Daniel.

## Slide 2
SECTION 1: Project Selection
1.1 Project Title
Development Of an Integrated Agricultural Farm And Marketing Management System.
1.2 Industry
Agriculture And Information Technology
1.3 Definition Of a Project
A project is a temporary endeavor undertaken to create a unique product, service, or result. it has a defined beginning and end, clear objectives, and is delivered within constraints of time, cost and scope.
1.4 Project Description
This project focuses on the development of an integrated agricultural farm and marketing management system designed to improve farm operations, product management, sales tracking, customer communication, and agricultural product marketing. The system will help farmers manage records efficiently while connecting them directly with buyers through a digital platform.

## Slide 3
SECTION 2: Project Charter
PM Analysis- How to Approach the Charter
The project charter is the foundational document that formally authorizes the project and gives the PM
the authority to apply resources. For an system like agricultural and marketing plan in Nigeria, the
charter must do more than list basic facts it must articulate a compelling business case that justifies the investment to sponsors, align stakeholders on objectives from day one, and set clear, measurable success criteria that will later inform project evaluation.
Project Title Development of an Integrated Agricultural Farm and
Marketing Management System.
Project Sponsor De’Fakuns Foundation, Linkage Company.
Project Manager Opeyemi Daniel ( Junior Project Manager).
CHARTER ELEMENT DETAIL

## Slide 4
Project Start July 1, 2026
Project End Septemeber 2, 2026
Estimated Budget NGN 730,000
Business Case / Justification Agricultural businesses face several operational challenges includ-
ing poor record keeping, inefficient inventory management, lack of
direct market access, inaccurate sales tracking, and low communic-
ation between farmers and customers. Most small and medium-sca
le farmers still rely heavily on manual processes which often result
in errors, product wastage, and reduced profitability.
The proposed integrated agricultural farm and marketing manage
ment system will provide a centralized digital platform for managing
farm operations, tracking inventory, recording sales, managing cust
tomers, and promoting agricultural products online. This project
will improve operational efficiency, reduce manual errors, and
increase farmers’ access to wider markets.

## Slide 5
Project Objectives 1. Develop a centralized farm management system.
2. Improve farm record keeping and inventory management.
3. Enable farmers to market products digitally.
4. Improve communication between farmers and customers.
5. Generate automated reports for decision-making.
6. Reduce operational inefficiencies associated with manual systems.
High-Level Scope IN SCOPE: User registration and login system, Farm inventory
management, Product management module, Sales and Transaction
tracking, Customer management, Marketing dashboard, Reporting
and analytics, Database management, User training and deployment.
Project Assumptions - Internet access will be available.
- User possess basic digital literacy.
- The project budget will be approved.
- Required hardware and software resources are available.
- Stakeholders will actively participate during development.
Success Criteria The project will be considered successful if:
- The system is fully developed and deployed.
- User can manage farm records electronically.

## Slide 6
- Product marketing functions effectively.
- User satisfaction exceeds 90%.
- Manual record-keeping is significantly reduced.
Key Stakeholders - De’ Fakuns Foundation, Linkage Company: (Project Sponsor)
Provides funding and approval.
- Project Manager: Oversees project and execution.
- Developers: Build the system.
- Farmers: Primary users.
- Customers: Purchase farm products.
- Marketing Team: Promote products.
- IT Support Team: System maintenance.
Project Constraints - Limited project budget
- Time limitations
- Dependence on internet connectivity
- Limited technical skills among some users

## Slide 7
SECTION 3: Scope Baseline
PM Analysis- How to Approach Scope Management
Scope management for an agricultural farm and marketing plan is one of the most important project in the
country. Every stakeholder from the sponsors to speakers will have ideas about what to add. The PM’s role is
to define a clear boundary between what is in and out of scope, baseline it formally, and enforce it through the
change control process.
3.1 Project Scope Statement
The project involves the design, development, testing, and deployment of an integrated agricultural farm and
Marketing management system that enables efficient farm operation management and online agricultural pro
duct marketing.
The system will support inventory tracking, customer management, sales monitoring, product marketing, and
Report generation.
3.2 Project Deliverables
* Requirement analysis document
* System design document

## Slide 8
* Database design
* Fully functional software system
* User authentication module
* Farm inventory module
* Product marketing module
* Sales tracking module
* Reporting dashboard
* User manual
* Testing report
Deployment report
3.3 Out-of- Scope Items
This are excluded from the project:
Mobile banking integration
AI prediction systems
International product shipping
Cryptocurrency payment systems
Drone-based farm monitoring

## Slide 9
3.4 Work Breakdown Structure (WBS)
WBS ID Work Package Sub-Tasks/ Description
1.0 Project Initiation Proposal development, Project approval
2.0 Requirement Gathering Stakeholder interviews, Requirement documentation
3.0 System Design Database design, User interface, Architecture planning
4.0 System Development Frontend development, Backend development, Data implement
ation
5.0 Testing Unit testing, integration testing, User acceptance testing
6.0 Deployment System installation, User Training
7.0 Project Closure Documentation, Final review, Project handover

## Slide 10
SECTION 4: Schedule Plan
PM Analysis- How to Approach Scheduling
Scheduling an agricultural farm and marketing plan is fundamentally different from scheduling any project many
Work streams run in parallel. The PM must work backwards, mapping every dependency to ensure nothing
Collapses the critical path.
Task Start Date End Date Duration Dependencies Milestone Date
Project Proposal July 1 July 5 5 Days None Project Approval July 5
Requirement Gathering July 6 July 12 7 Days Proposal
System Design July 13 July 20 8 Days Requirements Design Completion July 20
Database Design July 15 July 22 8 Days System Design
System Development July 21 August 20 30 Days Design Development Comp August 20
letion

## Slide 11
Testing August 21 August 28 8 Days Development Test Completion August 28
User Training August 29 August 30 2 Days Testing
Deployment August 31 Sept 2 3 Days Training Deployment Sept 2
Completion
Project Closure Sept 3 Sept 5 3 Days Deployment

## Slide 12
SECTION 5: Cost Baseline
PM Analysis- How to Approach Cost Management
For an agricultural farm and marketing plan, cost management is uniquely challenging because revenue (sponsor
ship and sales) and expenditure happen simultaneously and influence each other. The PM must maintain a live cost
model that tracks both inflows and outflows, not just expenditure alone.
Task Estimated Cost (NGN)
Requirement Analysis 50,000
System Design 80,000
Database Development 70,000
Software Development 250,000
Testing 70,000
Deployment 50,000

## Slide 13
Training 40,000
Documentation 30,000
Contingency Reserve 40,000
Management Reserve 50,000
Total Budget 730,000

## Slide 14
SECTION 6: Stakeholder Engagement & Communication Plan
PM Analysis- How to Approach Stakeholder Management
The PM is simultaneously managing paying sponsors, high-profile speakers, a government partner and vendors.
Stakeholder management in project management involves identifying, analyzing, engaging, and monitoring indivi
duals or group who can affect or be affected by a project.
RACI Matrix
R= Responsible A= Accountable C= Consulted I= Informed
Activity PM (Daniel) Developers Farmers Sponsor
Requirement Gathering A R C I
System Design A R I I
Development C R I I
Testing A R C I
Deployment A R C I

## Slide 15
Stakeholder Interest Level Influence Level Communication Method Frequency
Project Sponsor High High Meetings Weekly
Farmers High Medium Training Sessions Bi- Weekly
Customers Medium Low Email/ SMS Monthly
Developers High High Team Meetings Daily
Marketing Team Medium Medium

## Slide 16
SECTION 7: Risk Management Plan
PM Analysis- How to Approach Risk Management
Risk management for an agricultural farm and marketing plan needs the right management to put the right people in the right positions. Many farms fail because they focus only on production and ignore marketing, a PM should ensure the farm products actually reach buyers profitably.
Risk Probability Impact Mitigation Strategy
Budget Overrun Medium High Strict cost monitoring
Delayed Development Medium High Proper scheduling
System Failure Low High Frequent Testing
Poor Internet Access Medium Medium Offline support features
User Resistance Medium Medium User training programs
Data Loss Low High Database backups

## Slide 17
Risk Response Strategies
Risk Avoidance
Proper planning will reduce avoidable risks.
Risk Mitigation
Frequent testing and monitoring will reduce project issues.
Risk Transfer
External technical support may be outsourced if necessary.
4. Risk Acceptance
Minor unavoidable risks will be monitored and managed.

## Slide 18
SECTION 8: Quality Management & Change Control
PM Analysis- How to Approach Quality Management
Quality management in agricultural farm and marketing plan is creating a system that ensures your farm products
are consistently good, safe, profitable, and trusted by customers. Good records help monitor performance and improve quality. Quality management should support marketing because customer buy trusted products.
Quality Management Plan
To ensure project quality, the following measures will be implemented:
Regular code reviews
System testing
- User acceptance testing
Performance evaluation
Continuous monitoring
Stakeholder feedback sessions

## Slide 19
Quality Standards
The systems must:
Function without critical errors
Provide accurate reports
Maintain data security
Be user-friendly
Meet Stakeholder requirements
Change Management Plan
All project change will follow the process below:
Change request submission
Change impact analysis
Approval by project manager
Stakeholder communication
Implementation of approved Changes
Documentation update

## Slide 20
SECTION 9: Governance, PMO Structure & development Approach
PM Analysis- How to Approach Governance
Governance in an agricultural farm and marketing plan is creating a clear system for decision-making, accountability, supervision, communication, and compliance within the farm business and its marketing activities. Governance requires written policies that guide activities.
Project Governance
The project will adopt a functional governance structure where project decision are coordinated through the project manager with oversight from the project sponsor
The governance structure ensures:
Accountability
Effective decision-making
Proper communication
Resource coordination

## Slide 21
PMO Structure
Selected PMO Type
Supportive PMO
Reason For Selection
A supportive PMO is suitable because it provides templates, guidance, documentation support, and best practices without excessive control over project activities.
Development Approach
Agile Methodology
Reason For Selection
Agile methodology is appropriate because:
It supports continuous improvement
Stakeholder feedback can be incorporated easily
Development occurs in manageable iterations.
It improves flexibility and adaptability.

## Slide 22
CONCLUSION
The development of an integrated agricultural farm and marketing management system will significantly improve agricultural operation through digital transformation. The project provides an efficient solution for managing farm
Records, inventory, customer, relationships, and product marketing.
By implementing proper project management practices including planning, scheduling, budgeting, stakeholder, engagement, risk management, quality assurance, and governance, the project is expected to achieve its objectives successfully while delivering value to farmers and customers alike.